## Third-Party
Type | Third-Party | Dataflow ID | Description | Triggering Action | Consequence of Service Failure | Risk of Failure | User Impact | Monitoring | Efforts to Mitigate in Case of Failure
JS | Google | NA | Analytics | Page load | Potential issues with page load times | low | low | Copperegg | Comment out javascript
API | Facebook | 7 | Facebook Connect API allows users to use their Facebook accounts to login | Connection attempt | Inability to determine who a user is | low | high | Custom Status check | Code should be architected wth sane fail conditions if user cannot be immediately identified
API | Facebook | 14 | Facebook Connect API pulls in photos and friend connections on page | Page load | Inability to display/determine user's friends | low | low | Custom Status check | Code and UX should be architected wth sane fail conditions if user's friends cannot be loaded with page

## Application
Type | Dataflow ID | Description | Used By | Triggering Action | Consequence of Service Failure | Risk of Failure | User Impact | Monitoring | Efforts to Mitigate in Case of Failure
Internal API | 16 | API used to register the vote | Desktop, mobile | User votes | Users unable to vote | low | very high | Copperegg/Monitorus | Check cache and DB connections
HTTP | 3 | HTTP request after call to FB API to log user in the DB | Desktop, mobile | User signup | User unable to register | low | very high | Copperegg/Monitorus | Check cache and DB connections

## Dataflow Diagram
DATA/APP FLOW DIAGRAM GOES HERE
(Be sure to number the decision and elements, to be tied into the risk matrix)